## Research Schedule
Grant Award Schedule
TASK | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES | Proposal Name: | Communicating Through the Eyes of a Child
Award Set Up | [7 empty] | Nickname: | C-TEC
Set up meeting with CCI Research Dean to go over project information and budget | Normal | In Progress | 2012-10-15 | 2012-10-15 | 50% | 0 |  | Submission Deadline: | November 1st, 2014
Forward to CCI Grants Analyst the award and project number | High | In Progress | 2012-09-10 | 2012-09-20 | 50% | 0 | Who is SRA or RF Officer? | PI: | John Smith
Set up meeting to go over Project Logistics with Grants Analyst (i.e. Discuss any Budget Changes, Appointments or Hiring, Subcontracts or Consultants, and if an Advance is needed) | High | In Progress | 2012-09-15 | 2012-10-18 | 75% | 0 | Consultant from Data Management Inc. | Contact Phone: | 850-555-5555
Fill out any forms needed prior to grant starting (ex. Budget Summary Form, CAS Exemption Form for budgeted items not normally allowed) | Normal | Complete | 2012-09-15 | 2012-10-11 | 100% | 1 | None needed | Contact E-Mail: | jsmith@noaddress.com
Confirm that IRB has been approved by FSU Institutional Research Board (if project includes human subjects) | Normal | Complete | 2012-09-15 | 2012-10-11 | 100% | 1 | Have confirmation e-mail
Award Management | [5 empty] | 0 |  | Proposal Amount: | 250000
Review Monthly Budget Reports and discuss issues or budget change, and assist Grants Analyst with filling out forms (ex. Budget Amendment, DOL, etc.) | High | In Progress | 2012-09-15 | 2012-10-11 | 50% | 0 |  | Funding Agency: | NIH
Review, each semester, appointments and appointment funding with Grants Analyst | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0 |  | Web link to Funding Agency | www.nih.gov
Submit reports or invoices to Funding Agency (if applicable) | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0
Renew annually project IRB status (if human subjects are involved in grant project) | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0 | Need to renew in November each year
Review SRAD Distribution (distributed in November) - if applicable | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0
Annual Award Requirements | [5 empty] | 0
Three (3) Months Prior, meet with Grants Analyst to finalize research and associated costs / products | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0
Three (3) Months Prior, apply for a No Cost Extension (NCE) - if applicable | High | In Progress | 2012-09-15 | 2012-10-11 | 75% | 0
One (1) Month Prior, follow up with Grants Analyst that outstanding or encumbered checks, purchase orders, and travel has cleared | High | In Progress | 2012-09-15 | 2012-10-11 | 75% | 0
Submit any final reports, data, etc. to funding agency | High | In Progress | 2012-09-15 | 2012-10-11 | 25% | 0
*(SRA / RF - Will require written confirmation at conclusion of grant project / award to close project) | [5 empty] | 0
Formulas:
DUE DATE = ToDoList[[#This Row],[START DATE ]]+10

## Proposal Contact Info
Agency Name | NIH
Contact Person: | Jane Johnson
Contact Phone: | 888-555-1222
Contact E-Mail: | jjohnson@nih.gov
FSU Research Contacts
138000
FSU - SRA Contact Name | Jan James
FSU - SRA Contact Phone | 644-8663
FSU - SRA Contact E-Mail | jjames@fsu.edu
OR
181000, 182000, 183000
FSU - SRA Contact Name | Kevin Eady
FSU - SRA Contact Phone | 644-8676
FSU - SRA Contact E-Mail | keady@fsu.edu
CRC
Patrice C. Williams | 645-5751 | pcwilliams@fsu.edu
Research Foundation
138000
FSU - RF Contact Name | Cathy Flynn
FSU - RF Contact Phone | 644-2130
FSU - RF Contact E-Mail | cflynn@fsu.edu
OR
181000, 182000, 183000
FSU - RF Contact Name | Tracie Blackwood
FSU - RF Contact Phone | 644-3981
FSU - RF Contact E-Mail | tblackwood@fsu.edu
CCI Research Personnel
Cherie Pagan, Grants Compliance Analyst | 644-4109 | research@cci.fsu.edu
Ellen Harman, Assistant Director | 644-8105 | Ellen.Harman@cci.fsu.edu
Dr. Julian Woods, Research Dean | 645-4972 | Juliann.Woods@cci.fsu.edu

## Acronymns
Acronyms
CAS Form | Cost Accounting Standards Form
SRA | Sponsored Research Administration
RF | Research Foundation
CRC | Council on Research and Creativity